## CHC Prioritized Objectives
CHC Annual Planning Priorities 2010-2011 - Update Oct 2010
P&PR Priority | Pres Cab Priority | Area (I,P,SS,AS) | Objective | Resource(s) | Cost | Ongoing/ One-time | Comments | Status as of Oct 2010
Operational Necessities
Theme: Safety | [6 empty] | Cabinet = green font
23 | 1 | AS | Objective 7.1: (M&O) Implement a safety training calendar, review safety plans for implementation, train all M&O staff in accordance with plans; further develop department specific plans. | Time & effort of Faciltiy Director | NC | NA | Mandated; needs to move up to 1. | Completed; however, adjustment of the calendar is underway and scheduled for completion by January 2011
23 | 2 | I | 3.6 Implement the Safety Plan as it applies to Instruction. | VPI and Deans time and effort and funds for fit testing | 5000 | Ongoing |  | Respiratory Fit planning is underway. Preliminary procedures have been established. $700 set aside to purchase masks for instructors. Biology lab tech serves as chair of the on-campus safety committee.
23 | 3 | SS | Objective 5.5: Ensure a safe environment for students and staff | None | 0 | NA |  | Partially complete and ongoing: A&R, Student Life, and EOPS have reduced clutter. All SS staff have participated in the required safety training provided by the district.
Theme: Infrastructure for New and Existing Facilities
1 | 4 | AS | Objective 15.1: (M&O) Abide to required laws/fire codes in operation of Aquatic Center and LRC | Increase Ongoing general funds for LRC and AC fire alarm monitoring, testing, service, and testing of fire extinguishers | 8900 | Ongoing | LRC receives higher priority than pool due to benefit to students. Must be done. | Completed
1 | 5 | AS | Objective 15.2: (M&O) Abide to state elevator regulations in maintenance and certification of new elevators in the AC and LRC | Increase Ongoing general funds for outside contracts/agreements, permit fees, and maintenance and repair for elevators in AC & LRC | 17616 | Ongoing | Must be done. Majority of cost in 11-12. | Completed
1 | 6 | AS | Objective 15.3: (M&O) Abide to SCAQMD regulations in obtaining permits and annual testing on new LRC equipment | Increase Ongoing general funds for annual permit fees and testing for equipment installed in the LRC | 2000 | Ongoing | Must be done. Majority of cost in 11-12. | Completed; Permit to be posted on LRC Generator
1 | 7 | AS | Objective 15.4: (AS) Provide water, electricity and natural gas for new and existing facilities | Obtain and maintain ongoing funds for water, electricity, and gas | 361465 | Ongoing | Does not include savings from solar. Will be closer to $150,000. | Funded; Analysis of expenses is ongoing
1 | 8 | P | 2.1: Ensure that new and existing buildings function at an optimal level. | General Fund Measures M and P; Pool Support | 200000 | Ongoing | Staffing and maintenance of the new buildings. Custodial and Maintenance.
Theme: Institutionalize Title V Grant
3 | 9 | P | 1.1: Institutionalize the Title V Grant positions. | General Fund | 250000 | Ongoing | Instructional Assessment Specialist, Activity Director/Student Intervention Specialist, Development Studies Specialis, Web Developer, and Administrative Secretary; Resource Development positions. | All positions institutionalized
Additional Priorities
Theme: Contingency Fund
NA | 10 | President's Cabinet | Establish a campus contingency fund of 1/2% of total budget and review annually | General Fund | 90000 | Ongoing | The establishment of a contingecy fund will allow for unexpected costs that occur each year. | A contingency fund has been established as part of the President's budget
Theme: Institutionalize Categorical Student Services
2 | 11 | SS | Objective 5.1: (Assessment) Engage in planning to restore funds or reallocate responsibility for categorical services | Assessment test units for Matriculation. Campus wide responsibility. | 16800 | Ongoing | Matriculation requires 2400 test units per year to provide assessment services to CHC students. High priority. | Funded, additional planning required: Sufficient test units for 2010-2011 were purchased using Matriculation dollars. Planning will incorporate additional funding sources, including gifts and grants.
2 | 12 | SS | Objective 5.1: (EOPS) Engage in planning to restore funds or reallocate responsibility for categorical services | Adjunct Counselors for the EOPS program | 42823 | Ongoing | A reduction in EOPS funding has eliminated the budget for adjunct counselors. Students must wait longer to see a counselor for their mandated three contacts per semester. Cost effective way to provide services. | Funded on a temporary basis: The Santos Manual Student Success Partnership, a gift of $175,000, has provided supplemental counseling services to qualified EOPS students as well as students who do not meet the EOPS unit threshold.
2 | 13 | SS | Objective 5.1: (Counseling) Engage in planning to restore funds or reallocate responsibility for categorical services | Hourly Counselors, Counseling and Matriculation | 46000 | Ongoing | A severe reduction in the Matriculation budget impacted staffing by hourly counselors. Students must sometimes wait as long as 3 hours to see a counselor. Develop a pool of adjunct counselors for EOPS and Gen Coun. | Funded on a temporary basis: Hourly counselors are funded through the Santos Manuel Student Success Partnership, the Basic Skills Initiative. The program will continue to advocate for additional funding through PPR.
2 | 14 | SS | Objective 5.1:(Categorical) Engage in planning to restore funds or reallocate responsibility for categorical services | Backfill categorical salaries through 2011: DSPS Direcotr, EOPS Counselor, Student Services Instructional Assistant, EOPS 1/2-time Clerk | 280013 | One-time | The District has agreed to backfill categorical positions through the end of FY 2011. Planning and reallocation of duties will take place during 2010-2011. State funding will probably not continue. | Complete: SERPs and transfers have reduced the categorical obligation in DSPS, EOPS, and Matriculation.
2 | Future Priority | SS | Objective 5.1: (HWC) Engage in planning to restore funds or reallocate responsibility for categorical services | Adjunct Nurses for Health and Wellness Center | 59900 | Ongoing | The unit's budget was cut severely when it was determined that mandated costs would no longer be collected. The Center now operates solely on Student Health fees, with a reduction in services to students. As a CC we provide the first 2 years of education. Must be fiscally responsible and live within fees. Lower priority than listed. | Planned and in progress: The department is pursuing an alternate revenue stream in the form Family PACT, which will allow for MediCal billing of certain medical services
Theme: Targeted Focus Areas for Instruction
3 | 15 | I | 1.1 Foster growth of the Science Cluster to meet student needs | Personnel: $185,000 Equipment: $63,500 Building: $26 million |  | Both | Personnel costs exclude benefits Not all expenses would be needed in first year | Some equipment purchases were completed ($5186) A new lab tech position was created for Earth Sciences Retirement replacement positions were filled in Anatomy (faculty), Chem (lab tech), Physics (lab tech) The CHC Foundation is contributing approximately $15,000 for the purchase of supplies and equipment (Science Infusion Fund) The Facilities Master Plan was modified to move the Science building earlier in the queue Two modular labs are being built to meet classroom needs and will be in place by Fall 2011 A STEM grant is being prepared for submission in Fall 2010
3 | 16 | I | 1.2 Foster growth of the Public Safety & Health Cluster to meet student needs | Personnel: $129,000 Equipment: $93,900 Building: Unnknown |  | Both | Personnel costs exclude benefits Not all expenses would be needed in first year | The CHC Foundation contributed $5850 for equipment purchases
3 | 17 | I | 1.3 Foster growth of the Fine Arts Cluster to meet student needs | Personnel: $120,000 Equipment: $7,100 Events: $6,000 |  | Both | Personnel costs exclude benefits Not all expenses would be needed in first year | Some equipment purchases were completed ($5013) A grant ($10,000) was secured for the development of a communication and design program
3 | 18 | I | 1.4 Foster growth of Developmental Education and Support Services to meet student needs | Personnel: $348,000 Databases: $10,000 |  | Ongoing | Personnel costs exclude benefits Not all expenses would be needed in first year | A new Instructional Division was created centralizing developmental education and support services and a new dean was hired (start date Jan 2011) BSI funds of approximately $10,000 were committed to tutoring services
3 | 19 | I | 1.5 Foster growth of the Communication & Language Cluster to meet student needs | Personnel: $140,000 |  | Ongoing | Personnel costs exclude benefits Not all expenses would be needed in first year
3 | 20 | I | 1.6 Foster growth of Business & CIS Cluster to meet student needs | Personnel: $80,000 Equipment: $69,200 |  | Both | Personnel costs exclude benefits Not all expenses would be needed in first year | A faculty position (retirement replacement) in CIS is open and expected to be filled by Jan 2011
3 | 21 | I | 1.7 Foster growth of the Health/PE Cluster to meet student needs | Personnel: $245,000 |  | Ongoing | Personnel costs exclude benefits Not all expenses would be needed in first year | Equipment purchases were completed ($4964) Redesign of the PE/Athletics facilities is part of Facilities Master Plan and is underway
Theme: Planning, Program Review, and Reliable Data
4 | 22 | I | 2.1 Complete the cycle of Program Review and Planning for all areas of Instruction | Some Innovation funds needed for new projects/pilots VPI and Deans time and effort | Unnknown | One-time |  | Will be completed by Jan 2011
4 | 23 | I | 2.2 Complete outcome assessment cycles for all areas in Instruction | VPI and Deans time and effort | None | NA |  | All but two disciplines are involved in assessment 74% of courses have SLOs and assessment has occurred in over 45% ILOs are drafted and under review
4 | 24 | SS | Objective 4.1: Ensure that Student Services Units have access to data for planning and program improvement | None | 0 |  | Install SARS in all units, ensure cler definition of outcomes | In progress: To date, SARS has been installed in DSPS, EOPS, Counseling, and the Health and Wellness Center.
4 | 25 | SS | Objective 4.2:Continue to make progress on Student Services SAO/SLO measurement and use the data for program improvement | None | 0 | NA |  | Completed and ongoing: All Student Services units have completed at least one cycle of SAO/SLO assessment/evaluation. Next year, Elumen will be used to track progress for all SS units.
4 | 26 | SS | Objective 4.4: Complete the cycle of Program Review and Planning for all areas of Student Services | None | 0 | NA |  | Completed and ongoing: All SS units will have completed a full Program Review by the end of 2010-2011. In addition, all have participated in the annual planning process.
4 | 27 | P | 1.2: Increase the ability of CHC to use evidence to inform decision making. | Title V (future grant) BSI | 50000 | Ongoing | Hire a full-time Research Assistant | Grant was received and position will be funded in late Fall 2011
4 | 28 | P | 1.1: Increase access to data through the development of an Office of Research and Planning Web Page. | Title V Web Developer | 8000 | One-Time |  | Completed; no funds needed
Theme: Maintain New Facilities
5.1 | 29 | AS | Objective 15.5: (M&O) Obtain adequate custodial supplies to support the LRC and Aquatic Center | Ongoing general funds to increase custodial supply budget | 7216.8368 | Ongoing |  | Funding for custodial supplies is completed; analysis of appropriate funding ongoing
5.1 | 30 | AS | Objective 15.6: (M&O) Adequately clean the Aquatic Center and LRC when completed and turned over to the campus. | Increase Ongoing general funds to staff 2 custodial positions | 100170 | Ongoing |  | Custodial staff was increased by 2 FTE on 10/18/10
5.1 | 31 | AS | Objective 15.7: (M&O) Adequately maintain the pool and LRC when completed and turned over to the campus | Increase ongoing general funds to staff pool/maintenance technician | 61318 | Ongoing |  | Maintenance technician for the pool was not funded. However, 2 part-time pool attendants were hired on 10/18/10
5.1 | 31 | AS | Objective 15.8: (M&O) Adequately maintain newly constructed landscaping when turned over to the campus | Increase ongoing general funds to add 1 grounds worker | 48322 | Ongoing |  | This request was not funded; request will carry-over into 2011-2012 annual plan
5.1 | 33 | AS | Objective 15.9: (M&O) Provide adequate waste disposal services for newly constructed facilities | Increase Ongoing general funds for solid waste disposal and hazardous waste disposal associated with the new LRC and AC | 9000 | Ongoing |  | Funded
5.1 | 34 | AS | Objective 15.10: (M&O) Obtain additional supplies and maintenance contracts necessary to properly maintain the AC and LRC buildings and grounds | Ongoing general funds to increase maintenance and grounds supply and maintenance agreement budgets | 36500 | Ongoing |  | Funded
5.1 | 35 | AS | Objective 15.11: (M&O) Obtain custodial equipment required to support the functions of the LRC and Aquatic Center | One-time funds for three electric utility vehicles and cleaning equipment | 36800 | One-time |  | Partially funded; needs will be carried over into 2011-2012 annual plan
5.1 | 36 | AS | Objective 15.12: (M&O) Obtain additional maintenance & grounds equipment required to efficiently maintain new buildings and grounds | One-time funds for an electric utility vehicle | 12000 | One-time |  | Will be funded through parking fees; procurement of carts are pending
Theme: Maintain Existing Facilities
5.2 | 37 | AS | Objective 16.2: (M&O) Replace interior doors at PAC theater and in the black box room | One-time funds to contract replacement | 7350 | One-time | Could be an ORD funding project | Complete
5.2 | 38 | AS | Objective 13.1: (M&O) Establish and implement a preventative maintenance (PM) program | Time and effort of Facility Director & HVAC Technician | NC | NA |  | In process; this will carry into next year as time to work on the PM program is limited due to other priorities
Theme: Enrollment Management, Marketing, and Outreach
6 | 39 | SS | Objective 5.4: Work cooperatively with campus entities to plan and implement a systematic approach to Enrollment Management | None | 0 | NA |  | The Enrollment Management Committee is meeting to revise the three-year plan and to align it with the college QEI's. The plan will be completed by December, 2010.
6 | 40 | P | 4.1: Establish an infrastructure to coordinate marketing, outreach, and partnerships with community institutions and organizations. |  | 100000 | Ongoing | Create and fill a position for outreach/marketing coordination. | Position filled Sept 2010
Theme: Emergency Procedures
7 | 41 | AS | Objective 11.1: (M&O) Establish emergency procedures and assignments for fire alarm procedures, elevator inspection, fire, and building clearing in the event of disaster. | Time & effort of Faciltiy Director | NC | NA |  | In process; this will carry into next year as time to work on the emergency procedures is limited due to other priorities
Theme: Quality Counseling Services
8 | 42 | SS | Objective 2.1: (Counseling - Adjunct) Provide an exemplary level of counseling support to CHC students | Adjunct Counselors for Counseling (to replace a SERP retirement in 2008) | 50000 | Ongoing | A retirement was not replaced, causing a reduction in service to students. Not a SERP replacement, maintenance of services. | This will be mitigated in part by the hiring of a new Transfer Coordinator/Counselor, funded through Title V.
Budget Management
9 | 43 | I | 3.1 Evaluate all budgets and adjust resources as needed and where possible |  |  |  | Items 36 and 40 were consolidated with item 9 because they all deal with budget management and do not require additional resources | Completed as part of developmental budgets in Spring 2010 and will continue
36 | 44 | SS | Objective 5.7: Improve budget management in all SS units | None | 0 | NA |  | In progress, ongoing: SS unit leaders engage in dialogue with deans and the VPSS regardiing budget development and expenditures. Expenditures are approved by the supervisor and the VPSS.
40 | 45 | P | 3.2: Develop adequate budgets for the areas reporting to the President. |  | 0 | NA | Creating of three new budgets in the ORD, ORP, and TS | These budgets were established as part of the developmental budget process
Theme: Facilities Master Plan
10 | 46 | AS | Objective 14.1: (M&O) Work with District, consultants, and campus administration on implementation of construction plan | Time & effort of Faciltiy Director | NC | NA |  | Ongoing; Parking Lot, Access and Lighting Project, Library Demo, Science Modulars, Science Bldg programming, Student Center programming, and Wellness Pool construction are scheduled
10 | 47 | AS | Objective 12.1: (M&O) Develop a written policy for the issuance of keys and the standards for future construction and changes in door hardware | Time & effort of Faciltiy Director | NC | NA |  | Ongoing--the first phase of implementation will begin fall 2010 with the keying of the LRC and Aquatics Center
10 | 48 | AS | Objective 5.1: (Administrative Services) Install an effective marquee for CHC | Funding for purchase and installation of marquee | 30000 | One-time |  | In process - the marquee will be installed as part of the Parking Lot and Lighting Project
10 | 49 | I | 3.2 Participate in the modification of and help manage the Facilities Master Plan | VPI and Deans Time and Effort Bond Funds | Unknown | NA |  | Priorities list developed in Spring 2010 and will be updated annually
10 | 50 | P | 1.3: Re-establish Campus Data Center to new LRC and prepare for demolition of existing Library. |  | 0 | NA |  | Scheduled for Spring 2011
10 | 51 | P | 3.1: Refurbish old buildings to be energy and space efficient. | Measures M and P | 100000 | One-Time |  | Some remodeling and refurbishing are included in the Measure M Bond
30 | 52 | SS | Objective 5.6: Develop a vision for the new Student Services/Campus Center buliding(s) and ensure full participation of SS staff in planning | None | 0 | NA |  | Scheduled for Spring 2011
Theme: Technology
11 | 53 | P | 1.2: Maintain established equipment and software standards. | General Fund | 14000 | Ongoing | Training and support for new productivity software. DETS will provide resources for these three objectives. | Standards have been implemented and are being reviewed and updated as needed Central core will meet standards by Summer 2011
11 | 54 | P | 1.4: Virtualize servers to operate on a single robust platform. |  | 0 | NA |  | Proceeding on schedule with about 50% completed
11 | 55 | P | 1.1: Complete Campus-Wide wireless coverage. |  | 0 | NA | Provide better student experience and access to the internet. | Nearly all of interior structures have wireless coverage and exterior student assembly areas (e.g. quad)
Theme: Online Access for Students
12 | 56 | SS | Objective 1.1: Increase student access to and knowledge of college resources and opportunities | Online Orientation | 45000 | One-time | Will seek support from Basic Skills Initiative | Planned, partially funded: About 50% of the cost of online Orientation were sought and granted through the BSI. The remaining 50% will be requested through the Title V grant.
Theme: Grants
13 | 57 | I | 3.3 Seek and obtain appropriate grants | Funds for a contract grant writer VPI, Deans, ORP and ORD Time | 25000 | One-time | Seek contract grants writer for these two objectives. | New Title V Grant received ($3.1 million over 5 years) Grants Office will be establised as part of Title V Grant STEM grant will be submitted in Fall 2010 CIS/Arts Grant received ($10,000)
13 | 58 | SS | Objective 5.2: Seek alternative revenue streams to support the restoration, enhancement, and expansion of Student Services | Time only | 0 | NA |  | In progress. Examples are Title V (transfer), Basic Skills Initiative (online Orientation), Santos Manuel Band of Mission Indians.
Theme: Transfer Programs and Services
14 | 59 | I | 1.10 Expand the Honors program | On-going General Funds Grant Funds | 6000 | Ongoing |  | Title V Grant includes $175,000 to help fund Coordinator position
14 | 60 | SS | Objective 3.1: (Transfer Ctr Coord) Plan, fund, and promote a full-service Transfer Center | Fulltime Transfer Center Coordinator | 83500 | Ongoing | Possible Title V funding | Planned and funded: Title V grant will fully fund this full-time Coordinator/Counselor.
14 | 61 | SS | Objective 3.1: (Transfer Ctr Clerial) Plan, fund, and promote a full-service Transfer Center | Fulltime Clerical Support, Transfer Center | 42500 | Ongoing | Possible Title V funding | Planned and funded: A full-time secretary assigned to the Project Director will perform secretarial tasks for the Transfer Center as well as other T5 functions and activities.
14 | 62 | SS | Objective 3.1: Plan, fund, and promote a full-service Transfer Center | Transfer Center computers | 10500 | One-time | Possible Title V funding | Planned and funded: A fully equipped Transfer Center is planned. Title V grant funds will be used for the purchase of a mobile cart as well as computers and software for transfer.
14 | 63 | SS | Objective 3.3: Increase transfer preparedness of students at feeder high schools | None | 0 | NA |  | In progress: The Dean of Matriculation has been working with a CSU task group on the implementation of the Early Assessment Program.
Theme: Equipment Plan
15 | 64 | I | 3.4 Create an Equipment Inventory, Maintenance, and Replacement Plan | Instructional Staff time and effort Equipment Funds Existing Equipment Needs: $28,500 | 100000 | Ongoing | $100,000 per year would fund equipment plan | Tech Plan is in place, but no funding available Equipment Inventories are
15 | 65 | P | 2.2: Develop a consistent funding source for data projector replacement lamps. | District General Funds | 13500 | Ongoing | DETS will provide funding. | Funding has not been identified
Theme: Emergency Devices
16 | 66 | AS | Objective 16.1: (M&O) Install emergency lowering devices in LADM, CHS, SSB and PAC elevators | One-time funds to contract installation | 38643 | One-time |  | Not funded - will roll over into 2010-2011 annaul plan
Theme: Student Involvement
17 | 67 | SS | Objective 1.2: Increase student involvement in co-curricular activities | Student Center Specialist | 67788 | Ongoing | Would be funded by Student Center Fees | Not funded: will continue to monitor the level of funding available for this position.
Theme: Perkins Plan
18 | 68 | I | 2.3 Review and revise the Perkins Plan | Perkins Funds; VPI and CTE Dean time and effort | None | Ongoing |  | Completed
Theme: Student Diversity
19 | 69 | SS | Objective 2.2: Engage in research, planning, and advocacy to address the needs of a diverse CHC student population | None | 0 | NA |  | Ongoing. Some campus-wide events are schedueld to honor diverse cultures including Native American Day, Black History Month, etc. The Office of Research has completed a study on student diversity and distance education. The PPR process elicits iinformation about the demographic makeup of students in specific units. Much more needs to be done.
Theme: External Partners
20 | 70 | I | 1.12 Respond to requests from and build relationships with External Partners | Perkins Funds, Foundation Funds, General Funds | Unknown | Ongoing |  | Established partnerships continue. Some new partnerships have been established including the City of Yucaipa. Partnerships with CSUSB have expanded.
20 | 71 | SS | Objective 3.2: Increase articulation with four-year colleges and universities | None | 0 | NA |  | Included as a goal in the Title V grant Work has begun on SB1440
Theme: Innovative Teaching and Best Practices
21 | 72 | I | 1.8 Manage the implementation of Learning Communities | BSI funds, Title V funds, VPI and Deans time and effort | 15000 | Ongoing | These three objectives serve as pilots for innovative teaching practices | Continuing to improve scheduling process LCs will be part of the new Dean's responsibilities
21 | 73 | I | 1.9 Implement Instructional Activities on the BSI Plan | BSI funds, VPI and Deans time and effort | 20000 | Ongoing |  | Some completed, others underway
21 | 74 | SS | Objective 2.1: (Counseling- Hourly) Provide an exemplary level of counseling support to CHC students | Hourly Counselor to support Learning Communities | 32000 | Ongoing | Funding was provided in 2009-2010 by the Basic Skills Initiative | Partially complete and ongoing: BSI continues to fund a part-time counselor for Learning Communities.
Theme: Online Access for Students
22 | 75 | AS | Objective1.1: (Comm) Implement system for purchasing parking permits online | Ongoing funding for contracting online services | 3000 | Ongoing |  | Completed
22 | 76 | AS | Objective 4.2: (Bookstore) Continued development of the Bookstore’s webpage to improve the online sales and services of the website and maintain current/updated information. | No additional resources required | NC | NA |  | Ongoing
22 | 77 | SS | Objective 5.3: Expand the online Student Services infrastructure | None | 0 | NA |  | Partially complete and ongoing. WebAdvisor, online registration, online BOG, and other services are in progress. RSS and Twitter feeds have been created for all Student Services units.
22 | 78 | SS | Objective 2.3: Deliver effective services to online and evening students | None | 0 | NA |  | Partially complete and ongoing. Online counseling has been implemented and all websites updated. A representative from most SS units has undergone SiteCore training.
Theme: Input and Shared Governance
24 | 79 | AS | Objective 6.1: (AS) Reduce Dissatisfaction Level to 15% on Administrative Services Employee Satisfaction Survey Question “Your ability to provide input into issues that affect you.” | No additional resources required | NC | NA |  | Perform survey and analyze results - Planned for Spring 2011
24 | 80 | AS | Objective 6.2: (M&O) Reduce Dissatisfied in the department to 15% on the Administrative Services Employee Satisfaction Survey Question “Your ability to provide input into issues that affect your work.” | Time & effort of Faciltiy Director | NC | NA |  | Perform survey and analyze results - Planned for Spring 2011
24 | 81 | AS | Objective 4.1: (Cafeteria) Maintain existing service levels to enable an 85% combined “agree” and “strongly agree” on the Annual POS Survey | No additional resources required | NC |  |  | Perform survey and analyze results - Planned for Spring 2011
24 | 82 | AS | Objective 3.1: To decrease to 20% of “disagree” opinions on the Annual Facilities Use Satisfaction Survey | Depending on discussions, additional funding may be required for scheduling software improvements | TBD | One-time |  | Perform survey and analyze results - Planned for Spring 2011
24 | 83 | SS | Objective 4.3: Ensure that SS staff participate fully in shared governance opportunities, and have the opportunity to work collaboratively with other campus entites | None | 0 | NA |  | Ongoing and partially complete: Participation in governance committees is tracked by the VPSS and by Crafton Council. Both the President and the VPSS have encouraged staff participation in governance opportunities.
24 | 84 | SS | Objective 1.3: Ensure that students participate fully in shared governance opportunities, and have the opportunity to work collaboratively with other campus entites | None | 0 | NA |  | Ongoing and partially complete: Org Handbook includes tips for student retention on committees. Students have been assigned to most participative governance committees and a mentor assigned.
Theme: Communication
25 | 85 | I | 2.4 Continue to implement and assess improved communication methods and practices | VPI and Deans time and effort | None | NA
25 | 86 | SS | Objective 4.5: Ensure a high level of communication and collaboration among Student Services staff | None | 0 | NA |  | Ongoing: The Student Services Council meets twice monthly; the managers meet twice monthly, and the entire SS staff meets once per month. In addition, email and direct contact is used to keep members in the loop.
Theme: Year-long Scheduling
26 | 87 | I | 3.5 Pilot and assess year-long scheduling | VPI, Deans, and Chairs time and effort | Unknown | One-time |  | First cycle completed Fall 2010 and will be assessed in early Spring 2011
Theme: Cafeteria
27 | 88 | AS | Objective 2.2: (Cafeteria) Improve financial performance of Cafeteria operations to the point where expenses equal revenues by 2012 | Depending on discussions and the direction chosen, there may not be a need for funds for the assessment, or there may be a need for funds for a consultant to perform the assessment. | 0-15,000 | One-time |  | Improvements and analysis of the cafeteria is ongoing
Theme: Audio Visual
28 | 89 | P | 2.1: Provide consistent support for Instructional and Non-Instructional A/V needs. |  | 50000 | Ongoing | Hire a full-time A/V Specialist. | Funding not identified Cross training is occuring with Tech Services to improve coverage
Theme: Bookstore
29 | 90 | AS | Objective 4.3: (Bookstore) Develop a “Guarantee” Book Buyback program to assist students with the cost of textbooks and enable the Bookstore to be more competitive with online competitors. | The hiring of FWS/Cal Work students to help with the workload needed to setup/maintain the program. | NC | NA |  | Ongoing Program piloted with Santos Manuel grant
Theme: Professional Development
31 | 91 | I | 1.14 Identify and Fund Professional Development Activities for all employees | Perkins Funds, Prof Dev Funds, BSI Funds, General Funds, Committee or Coordinator time | 10000 | Ongoing
Theme: Catalog
32 | 92 | I | 2.5 Revise the catalog to be more user-friendly | VPI and Deans time and effort | None | NA |  | Completed
Theme: New Instructional Programs
33 | 93 | I | 1.11 Explore new programs | Perkins Funds, Grants, General Funds, VPI and Deans time and effort | Unknown | Ongoing |  | The EMPC will provide input in Spring 2011
Theme: Employee Evaluation
34 | 94 | I | 1.13 Effectively evaluate all employees | VPI and Deans time and effort | None | NA |  | Ongoing
34 | 95 | SS | Objective 5.8: Set clear performance expectations and evaluate all employees | None | 0 | NA |  | In progress: evaluations dates have been placed on a spreadsheet and are actively monitored by the VPSS.
Theme: Alumni
35 | 96 | P | 1.1: Establish an ongoing system for engaging alumni in an effort to harness their goodwill and future generosity. | Title V COOP General Fund | 75000 | Ongoing | Hire a full-time Alumni Coordinator | All alumni names have been uploaded and the first marketing piece will be mailed in Spring 2011.
Theme: Effieciency and Customer Service
37 | 97 | AS | Objective 2.1: (CBO) Maintain timeliness for deposits from Cafeteria, Library (fees and copies), Admissions, CDC, Campus Clubs, Communications, and Custodial so that 98% of funds are receieved/deposited with CBO within 24 Hours | No additional resources required | NC | NA |  | Meeting established objective--ongoing
37 | 98 | AS | Objective1.2: (CBO) Enhance communication with, and access for customers resulting in improved customer service | Replace bullet-proof glass with one that has hearing and sound enhancements; Redesign customer counter to include 2 money drawers and 2 computers | TBD | NA |  | Not funded - will roll over into 2010-2011 annaul plan
37 | 99 | AS | Objective 8.1: (M&O) Improve Mostly Satisfied and Very Satisfied to 75% on the Campus Climate Survey Question “Maintenance and upgrades of all campus buildings.” | Time and effort of Facility Director | NC | NA |  | Perform survey and analyze results - Planned for Spring 2011
37 | 100 | AS | Objective 9.1: (M&O) Maintain Satisfied and very Satisfied at 85% on the Campus Climate Survey Question “Pleasantness and maintenance of grounds despite impact of construction.” | Time and effort of Facility Director; Grounds personnel daily maintenance effort | NC | NA |  | Perform survey and analyze results - Planned for Spring 2011
38 | 101 | AS | Objective 18.1: (CBO) Procure a counting safe | One-time funds to procure counting safe | 15000 | One-time |  | Safe has been procured and is in use
39 | 102 | AS | Objective 17.1: (M&O) Purchase a laptop computer for the campus energy management system (HVAC Controls) | One-time funds to procure laptop computer | 2100 | One-time |  | Not funded - will roll over into 2010-2011 annaul plan
* | Part of regular duties | I | 3.7 Assess and adjust organizational structure to increase capacity |  |  |  |  | Completed for 2010 - 2011 and will be repeated for 2011 - 2012

## Area Prioritized Objectives
Area (President, Instruction, Student Services, Administrative Services) Annual Planning Priorities 2010-2011
Objectives
Dept. Priority | President | CHC Priority | Obj # | Instruction | CHC Priority | Student Services | CHC Priority | Administrative Services | CHC Priority
1 | 1.1: Institutionalize the Title V Grant positions. | 3 | 1.1 | Foster growth of the Science Cluster to meet student needs | 3 | Objective 5.1:(Categorical) Engage in planning to restore funds or reallocate responsibility for categorical services | 2 | Objective 15.1: (M&O) Abide to required laws/fire codes in operation of Aquatic Center and LRC | 1
2 | 4.1: Establish an infrastructure to coordinate marketing, outreach, and partnerships with community institutions and organzizations. | 6 | 1.2 | Foster growth of the Public Safety & Health Cluster to meet student needs | 3 | Objective 5.1: (HWC) Engage in planning to restore funds or reallocate responsibility for categorical services | 2 | Objective 15.2: (M&O) Abide to state elevator regulations in maintenance and certification of new elevators in the AC and LRC | 1
3 | 2.1: Ensure that new buildings function at an optimal level. | 1 | 1.3 | Foster growth of the Fine Arts Cluster to meet student needs | 3 | Objective 5.1: (EOPS) Engage in planning to restore funds or reallocate responsibility for categorical services | 2 | Objective 15.3: (M&O) Abide to SCAQMD regulations in obtaining permits and annual testing on new LRC equipment | 1
4 | 2.1: Provide consistent support for Instructional and Non-Instructional A/V needs. | 28 | 1.4 | Foster growth of Developmental Education and Support Services to meet student needs | 3 | Objective 5.1: (Assessment) Engage in planning to restore funds or reallocate responsibility for categorical services | 2 | Objective 15.4: (AS) Provide water, electricity and natural gas for new facilities | 1
5 | 1.1: Establish an ongoing system for engaging alumni in an effort to harness their goodwill and future generosity. | 35 | 1.5 | Foster growth of the Communication & Language Cluster to meet student needs | 3 | Objective 5.1: (Counseling) Engage in planning to restore funds or reallocate responsibility for categorical services | 2 | Objective 15.5: (M&O) Obtain adequate custodial supplies to support the LRC and Aquatic Center | 5.1
6 | 1.2: Increase the ability of CHC to use evidence to inform decision making. | 4 | 1.6 | Foster growth of Business & CIS Cluster to meet student needs | 3 | Objective 2.1: (Counseling - Adjunct) Provide an exemplary level of counseling support to CHC students | 8 | Objective 15.6: (M&O) Adequately clean the Aquatic Center and LRC when completed and turned over to the campus. | 5.1
7 | 1.1: Increase access to data through the development of an Office of Research and Planning Web Page. | 4 | 1.7 | Foster growth of the Health/PE Cluster to meet student needs | 3 | Objective 2.1: (Counseling- Hourly) Provide an exemplary level of counseling support to CHC students | 21 | Objective 15.7: (M&O) Adequately maintain the pool and LRC when completed and turned over to the campus | 5.1
8 | 1.2: Maintain established equipment and software standards. | 11 | 2.1 | Complete the cycle of Program Review and Planning for all areas of Instruction | 4 | Objective 1.1: Increase student access to and knowledge of college resources and opportunities | 12 | Objective 15.8: (M&O) Adequately maintain newly constructed landscaping when turned over to the campus | 5.1
9 | 1.3: Re-establish Campus Data Center to new LRC and prepare for demolition of existing Library. | 10 | 2.2 | Complete outcome assessment cycles for all areas in Instruction | 4 | Objective 4.1: Ensure that Student Services Units have access to data for planning and program improvement | 4 | Objective 15.9: (M&O) Provide adequate waste disposal services for newly constructed facilities | 5.1
10 | 3.2: Develop adequate budgets for the areas reporting to the President. | 40 | 3.1 | Evaluate all budgets and adjust resources as needed and where possible | 9 | Objective 3.1: (Transfer Ctr Coord) Plan, fund, and promote a full-service Transfer Center | 14 | Objective 15.10: (M&O) Obtain additional supplies and maintenance contracts necessary to properly maintain the AC and LRC buildings and grounds | 5.1
11 | 1.4: Virtualize servers to operate on a single robust platform. | 11 | 3.2 | Participate in the modification of and help manage the Facilities Master Plan | 10 | Objective 3.1: (Transfer Ctr Clerial) Plan, fund, and promote a full-service Transfer Center | 14 | Objective 11.1: (M&O) Establish emergency procedures and assignments for fire alarm procedures, elevator inspection, fire, and building clearing in the event of disaster. | 7
12 | 2.2: Develop a consistent funding source for data projector replacement lamps. | 15 | 3.3 | Seek and obtain appropriate grants | 13 | Objective 5.2: Seek alternative revenue streams to support the restoration, enhancement, and expansion of Student Services | 13 | Objective 2.1: (CBO) Maintain timeliness for deposits from Cafeteria, Library (fees and copies), Admissions, CDC, Campus Clubs, Communications, and Custodial so that 98% of funds are receieved/deposited with CBO within 24 Hours | 37
13 | 3.1: Refurbish old buildings to be energy and space efficient. | 10 | 3.4 | Create an Equipment Inventory, Maintenance, and Replacement Plan | 15 | Objective 1.2: Increase student involvement in co-curricular activities | 17 | Objective1.1: (Comm) Implement system for purchasing parking permits online | 22
14 | 1.1: Complete Campus-Wide wireless coverage. | 11 | 2.3 | Review and revise the Perkins Plan | 18 | Objective 3.1: Plan, fund, and promote a full-service Transfer Center | 14 | Objective 15.11: (M&O) Obtain custodial equipment required to support the functions of the LRC and Aquatic Center | 5.1
15 |  |  | 1.12 | Respond to requests from and build relationships with External Partners | 20 | Objective 2.2: Engage in research, planning, and advocacy to address the needs of a diverse CHC student population | 19 | Objective 15.12: (M&O) Obtain additional maintenance & grounds equipment required to efficiently maintain new buildings and grounds | 5.1
16 |  |  | 1.8 | Manage the implementation of Learning Communities | 21 | Objective 3.2: Increase articulation with four-year colleges and universities | 20 | Objective 14.1: (M&O) Work with District, consultants, and campus administration on implementation of construction plan | 10
17 |  |  | 1.9 | Implement Instructional Activities on the BSI Plan | 21 | Objective 5.3: Expand the online Student Services infrastructure | 22 | Objective 16.1: (M&O) Install emergency lowering devices in LADM, CHS, SSB and PAC elevators | 16
18 |  |  | 1.1 | Expand the Honors program | 14 | Objective 4.2:Continue to make progress on Student Services SAO/SLO measurement and use the data for program improvement | 4 | Objective 16.2: (M&O) Replace interior doors at PAC theater and in the black box room | 5.2
19 |  |  | 2.4 | Continue to implement and assess improved communication methods and practices | 25 | Objective 2.3: Deliver effective services to online and evening students | 22 | Objective 13.1: (M&O) Establish and implement a preventative maintenance (PM) program | 5.2
20 |  |  | 3.5 | Pilot and assess year-long scheduling | 26 | Objective 4.3: Ensure that SS staff participate fully in shared governance opportunities, and have the opportunity to work collaboratively with other campus entites | 24 | Objective 7.1: (M&O) Implement a safety training calendar, review safety plans for implementation, train all M&O staff in accordance with plans; further develop department specific plans. | 23
21 |  |  | 3.6 | Implement the Safety Plan as it applies to Instruction. | 23 | Objective 1.3: Ensure that students participate fully in shared governance opportunities, and have the opportunity to work collaboratively with other campus entites | 24 | Objective 18.1: (CBO) Procure a counting safe | 38
22 |  |  | 3.7 | Assess and adjust organizational structure to increase capacity | * | Objective 5.4: Work cooperatively with campus entities to plan and implement a systematic approach to Enrollment Management | 6 | Objective 12.1: (M&O) Develop a written policy for the issuance of keys and the standards for future construction and changes in door hardware | 10
23 |  |  | 1.13 | Effectively evaluate all employees | 34 | Objective 4.4: Complete the cycle of Program Review and Planning for all areas of Student Services | 4 | Objective 6.1: (AS) Reduce Dissatisfaction Level to 15% on Administrative Services Employee Satisfaction Survey Question “Your ability to provide input into issues that affect you.” | 24
24 |  |  | 1.14 | Identify and Fund Professional Development Activities for all employees | 31 | Objective 5.5: Ensure a safe environment for students and staff | 23 | Objective 6.2: (M&O) Reduce Dissatisfied in the department to 15% on the Administrative Services Employee Satisfaction Survey Question “Your ability to provide input into issues that affect your work.” | 24
25 |  |  | 1.11 | Explore new programs | 33 | Objective 4.5: Ensure a high level of communication and collaboration among Student Services staff | 25 | Objective 2.2: (Cafeteria) Improve financial performance of Cafeteria operations to the point where expenses equal revenues by 2012 | 27
26 |  |  | 2.5 | Revise the catalog to be more user-friendly | 32 | Objective 5.6: Develop a vision for the new Student Services/Campus Center buliding(s) and ensure full participation of SS staff in planning | 30 | Objective 4.1: (Cafeteria) Maintain existing service levels to enable an 85% combined “agree” and “strongly agree” on the Annual POS Survey | 24
27 | [5 empty] | Objective 3.3: Increase transfer preparedness of students at feeder high schools | 14 | Objective 5.1: (Administrative Services) Install an effective marquee for CHC | 10
28 | [5 empty] | Objective 5.7: Improve budget management in all SS units | 36 | Objective 3.1: To decrease to 20% of “disagree” opinions on the Annual Facilities Use Satisfaction Survey | 24
29 | [5 empty] | Objective 5.8: Set clear performance expectations and evaluate all employees | 34 | Objective 4.2: (Bookstore) Continued development of the Bookstore’s webpage to improve the online sales and services of the website and maintain current/updated information. | 22
30 | [7 empty] | Objective 4.3: (Bookstore) Develop a “Guarantee” Book Buyback program to assist students with the cost of textbooks and enable the Bookstore to be more competitive with online competitors. | 29
31 | [7 empty] | Objective1.2: (CBO) Enhance communication with, and access for customers resulting in improved customer service | 37
32 | [7 empty] | Objective 17.1: (M&O) Purchase a laptop computer for the campus energy management system (HVAC Controls) | 39
33 | [7 empty] | Objective 8.1: (M&O) Improve Mostly Satisfied and Very Satisfied to 75% on the Campus Climate Survey Question “Maintenance and upgrades of all campus buildings.” | 37
34 | [7 empty] | Objective 9.1: (M&O) Maintain Satisfied and very Satisfied at 85% on the Campus Climate Survey Question “Pleasantness and maintenance of grounds despite impact of construction.” | 37

## Sheet1
CHC Annual Planning Priorities 2010-2011
CHC Priority | Area (I,P,SS,AS) | Objective | Status as of 10/29/10
1 | AS | Objective 15.1: (M&O) Abide to required laws/fire codes in operation of Aquatic Center and LRC
1 | AS | Objective 15.2: (M&O) Abide to state elevator regulations in maintenance and certification of new elevators in the AC and LRC
1 | AS | Objective 15.3: (M&O) Abide to SCAQMD regulations in obtaining permits and annual testing on new LRC equipment
1 | AS | Objective 15.4: (AS) Provide water, electricity and natural gas for new facilities
1 | P | 2.1: Ensure that new buildings function at an optimal level.
2 | SS | Objective 5.1:(Categorical) Engage in planning to restore funds or reallocate responsibility for categorical services
2 | SS | Objective 5.1: (HWC) Engage in planning to restore funds or reallocate responsibility for categorical services
2 | SS | Objective 5.1: (EOPS) Engage in planning to restore funds or reallocate responsibility for categorical services
2 | SS | Objective 5.1: (Assessment) Engage in planning to restore funds or reallocate responsibility for categorical services
2 | SS | Objective 5.1: (Counseling) Engage in planning to restore funds or reallocate responsibility for categorical services
3 | I | 1.1 Foster growth of the Science Cluster to meet student needs
3 | I | 1.2 Foster growth of the Public Safety & Health Cluster to meet student needs
3 | I | 1.3 Foster growth of the Fine Arts Cluster to meet student needs
3 | I | 1.4 Foster growth of Developmental Education and Support Services to meet student needs
3 | I | 1.5 Foster growth of the Communication & Language Cluster to meet student needs
3 | I | 1.6 Foster growth of Business & CIS Cluster to meet student needs
3 | I | 1.7 Foster growth of the Health/PE Cluster to meet student needs
3 | P | 1.1: Institutionalize the Title V Grant positions.
4 | I | 2.1 Complete the cycle of Program Review and Planning for all areas of Instruction
4 | I | 2.2 Complete outcome assessment cycles for all areas in Instruction
4 | SS | Objective 4.1: Ensure that Student Services Units have access to data for planning and program improvement
4 | SS | Objective 4.2:Continue to make progress on Student Services SAO/SLO measurement and use the data for program improvement
4 | SS | Objective 4.4: Complete the cycle of Program Review and Planning for all areas of Student Services
4 | P | 1.2: Increase the ability of CHC to use evidence to inform decision making.
4 | P | 1.1: Increase access to data through the development of an Office of Research and Planning Web Page.
5.1 | AS | Objective 15.5: (M&O) Obtain adequate custodial supplies to support the LRC and Aquatic Center
5.1 | AS | Objective 15.6: (M&O) Adequately clean the Aquatic Center and LRC when completed and turned over to the campus.
5.1 | AS | Objective 15.7: (M&O) Adequately maintain the pool and LRC when completed and turned over to the campus
5.1 | AS | Objective 15.8: (M&O) Adequately maintain newly constructed landscaping when turned over to the campus
5.1 | AS | Objective 15.9: (M&O) Provide adequate waste disposal services for newly constructed facilities
5.1 | AS | Objective 15.10: (M&O) Obtain additional supplies and maintenance contracts necessary to properly maintain the AC and LRC buildings and grounds
5.1 | AS | Objective 15.11: (M&O) Obtain custodial equipment required to support the functions of the LRC and Aquatic Center
5.1 | AS | Objective 15.12: (M&O) Obtain additional maintenance & grounds equipment required to efficiently maintain new buildings and grounds
5.2 | AS | Objective 16.2: (M&O) Replace interior doors at PAC theater and in the black box room
5.2 | AS | Objective 13.1: (M&O) Establish and implement a preventative maintenance (PM) program
6 | SS | Objective 5.4: Work cooperatively with campus entities to plan and implement a systematic approach to Enrollment Management
6 | P | 4.1: Establish an infrastructure to coordinate marketing, outreach, and partnerships with community institutions and organzizations.
7 | AS | Objective 11.1: (M&O) Establish emergency procedures and assignments for fire alarm procedures, elevator inspection, fire, and building clearing in the event of disaster.
8 | SS | Objective 2.1: (Counseling - Adjunct) Provide an exemplary level of counseling support to CHC students
9 | I | 3.1 Evaluate all budgets and adjust resources as needed and where possible
10 | AS | Objective 14.1: (M&O) Work with District, consultants, and campus administration on implementation of construction plan
10 | AS | Objective 12.1: (M&O) Develop a written policy for the issuance of keys and the standards for future construction and changes in door hardware
10 | AS | Objective 5.1: (Administrative Services) Install an effective marquee for CHC
10 | I | 3.2 Participate in the modification of and help manage the Facilities Master Plan
10 | P | 1.3: Re-establish Campus Data Center to new LRC and prepare for demolition of existing Library.
10 | P | 3.1: Refurbish old buildings to be energy and space efficient.
11 | P | 1.2: Maintain established equipment and software standards.
11 | P | 1.4: Virtualize servers to operate on a single robust platform.
11 | P | 1.1: Complete Campus-Wide wireless coverage.
12 | SS | Objective 1.1: Increase student access to and knowledge of college resources and opportunities
13 | I | 3.3 Seek and obtain appropriate grants
13 | SS | Objective 5.2: Seek alternative revenue streams to support the restoration, enhancement, and expansion of Student Services
14 | I | 1.10 Expand the Honors program
14 | SS | Objective 3.1: (Transfer Ctr Coord) Plan, fund, and promote a full-service Transfer Center
14 | SS | Objective 3.1: (Transfer Ctr Clerial) Plan, fund, and promote a full-service Transfer Center
14 | SS | Objective 3.1: Plan, fund, and promote a full-service Transfer Center
14 | SS | Objective 3.3: Increase transfer preparedness of students at feeder high schools
15 | I | 3.4 Create an Equipment Inventory, Maintenance, and Replacement Plan
15 | P | 2.2: Develop a consistent funding source for data projector replacement lamps.
16 | AS | Objective 16.1: (M&O) Install emergency lowering devices in LADM, CHS, SSB and PAC elevators
17 | SS | Objective 1.2: Increase student involvement in co-curricular activities
18 | I | 2.3 Review and revise the Perkins Plan
19 | SS | Objective 2.2: Engage in research, planning, and advocacy to address the needs of a diverse CHC student population
20 | I | 1.12 Respond to requests from and build relationships with External Partners
20 | SS | Objective 3.2: Increase articulation with four-year colleges and universities
21 | I | 1.8 Manage the implementation of Learning Communities
21 | I | 1.9 Implement Instructional Activities on the BSI Plan
21 | SS | Objective 2.1: (Counseling- Hourly) Provide an exemplary level of counseling support to CHC students
22 | AS | Objective1.1: (Comm) Implement system for purchasing parking permits online
22 | AS | Objective 4.2: (Bookstore) Continued development of the Bookstore’s webpage to improve the online sales and services of the website and maintain current/updated information.
22 | SS | Objective 5.3: Expand the online Student Services infrastructure
22 | SS | Objective 2.3: Deliver effective services to online and evening students
23 | AS | Objective 7.1: (M&O) Implement a safety training calendar, review safety plans for implementation, train all M&O staff in accordance with plans; further develop department specific plans.
23 | I | 3.6 Implement the Safety Plan as it applies to Instruction.
23 | SS | Objective 5.5: Ensure a safe environment for students and staff
24 | AS | Objective 6.1: (AS) Reduce Dissatisfaction Level to 15% on Administrative Services Employee Satisfaction Survey Question “Your ability to provide input into issues that affect you.”
24 | AS | Objective 6.2: (M&O) Reduce Dissatisfied in the department to 15% on the Administrative Services Employee Satisfaction Survey Question “Your ability to provide input into issues that affect your work.”
24 | AS | Objective 4.1: (Cafeteria) Maintain existing service levels to enable an 85% combined “agree” and “strongly agree” on the Annual POS Survey
24 | AS | Objective 3.1: To decrease to 20% of “disagree” opinions on the Annual Facilities Use Satisfaction Survey
24 | SS | Objective 4.3: Ensure that SS staff participate fully in shared governance opportunities, and have the opportunity to work collaboratively with other campus entites
24 | SS | Objective 1.3: Ensure that students participate fully in shared governance opportunities, and have the opportunity to work collaboratively with other campus entites
25 | I | 2.4 Continue to implement and assess improved communication methods and practices
25 | SS | Objective 4.5: Ensure a high level of communication and collaboration among Student Services staff
26 | I | 3.5 Pilot and assess year-long scheduling
27 | AS | Objective 2.2: (Cafeteria) Improve financial performance of Cafeteria operations to the point where expenses equal revenues by 2012
28 | P | 2.1: Provide consistent support for Instructional and Non-Instructional A/V needs.
29 | AS | Objective 4.3: (Bookstore) Develop a “Guarantee” Book Buyback program to assist students with the cost of textbooks and enable the Bookstore to be more competitive with online competitors.
30 | SS | Objective 5.6: Develop a vision for the new Student Services/Campus Center buliding(s) and ensure full participation of SS staff in planning
31 | I | 1.14 Identify and Fund Professional Development Activities for all employees
32 | I | 2.5 Revise the catalog to be more user-friendly
33 | I | 1.11 Explore new programs
34 | I | 1.13 Effectively evaluate all employees
34 | SS | Objective 5.8: Set clear performance expectations and evaluate all employees
35 | P | 1.1: Establish an ongoing system for engaging alumni in an effort to harness their goodwill and future generosity.
36 | SS | Objective 5.7: Improve budget management in all SS units
37 | AS | Objective 2.1: (CBO) Maintain timeliness for deposits from Cafeteria, Library (fees and copies), Admissions, CDC, Campus Clubs, Communications, and Custodial so that 98% of funds are receieved/deposited with CBO within 24 Hours
37 | AS | Objective1.2: (CBO) Enhance communication with, and access for customers resulting in improved customer service
37 | AS | Objective 8.1: (M&O) Improve Mostly Satisfied and Very Satisfied to 75% on the Campus Climate Survey Question “Maintenance and upgrades of all campus buildings.”
37 | AS | Objective 9.1: (M&O) Maintain Satisfied and very Satisfied at 85% on the Campus Climate Survey Question “Pleasantness and maintenance of grounds despite impact of construction.”
38 | AS | Objective 18.1: (CBO) Procure a counting safe
39 | AS | Objective 17.1: (M&O) Purchase a laptop computer for the campus energy management system (HVAC Controls)
40 | P | 3.2: Develop adequate budgets for the areas reporting to the President.
* | I | 3.7 Assess and adjust organizational structure to increase capacity